## Gantt Chart
Task | Module | Start Date | End Date | Duration (days) | Status | Owner | Dependencies
Setup & Config | Project Setup | 2025-04-01 | 2025-04-01 | 1 | Done | Dev | None
QnA Module | AI Modules | 2025-04-01 | 2025-04-02 | 1.5 | Done | Dev | Setup
Explanation Module | AI Modules | 2025-04-02 | 2025-04-03 | 1.5 | Done | Dev | Setup
Quiz Module | AI Modules | 2025-04-03 | 2025-04-04 | 2 | Done | Dev | Setup
Summary Module | AI Modules | 2025-04-04 | 2025-04-05 | 1.5 | Done | Dev | Setup
Learning Path Module | AI Modules | 2025-04-05 | 2025-04-06 | 1.5 | Done | Dev | Setup
FastAPI Backend | Backend | 2025-04-06 | 2025-04-07 | 2 | Done | Dev | All Modules
Frontend HTML/CSS/JS | Frontend | 2025-04-07 | 2025-04-08 | 3 | Done | Dev | Backend
Automated Testing | Testing | 2025-04-08 | 2025-04-09 | 2 | Done | QA | Frontend+Backend
Manual Testing | Testing | 2025-04-09 | 2025-04-09 | 0.5 | Done | QA | Automated
Documentation README | Docs | 2025-04-09 | 2025-04-10 | 1 | Done | Dev | Testing
Screenshots | Docs | 2025-04-10 | 2025-04-10 | 0.5 | Done | Dev | Testing
DOCX Generation | Docs | 2025-04-10 | 2025-04-10 | 0.5 | Done | Dev | Screenshots
Phase-wise Docs | Docs | 2025-04-10 | 2025-04-11 | 1 | Done | Dev | DOCX
Voice Selection | Videos | 2025-04-11 | 2025-04-11 | 0.5 | Done | Dev | Docs
Demo Video | Videos | 2025-04-11 | 2025-04-11 | 1 | Done | Dev | Voice
Testing Video | Videos | 2025-04-11 | 2025-04-11 | 1 | Done | Dev | Demo Video
Final Checks & Push | GitHub | 2025-04-11 | 2025-04-11 | 1 | Done | Dev | Videos